School/College Name:	Happy Valley Primary School    	Location: Happy Valley

School Number/Catholic Ed. Number	_______________________________________________

Principal________________________________________________

| Core Team Members | Position in School |
| --- | --- |
|  | Principal Class (Assistant Principal) |
|  | Primary Welfare Officer |
|  | Health/PE/Personal/Soc learning Coordinator |
|  | Level /Team Representative (P-6) |

This School Drug Education Work Plan is designed to support the goals and key improvement strategies outlined in the School Strategic Plan and Annual Implementation Plan. In developing this plan, schools should consider a range of data and supporting documents to ensure strategies are evidence-based and appropriate to their school community. The plan utilises the national Principles for School Drug Education to assist schools plan their activities for continued improvement in drug education.

Goal: To continuously improve the quality of drug education in Victorian Schools to contribute to the reduction in the demand for and harms associated with drug use.

| ## Theme Area | Comprehensive and evidence based | Positive school climate and relationships | Targeted to needs and context | Effective Pedagogy |
| --- | --- | --- | --- | --- |
| Strengths | Where drug education is being taught in the school, State and Commonwealth resources are being utilised. | We promote a safe and supportive school environment. We promote and implement an effective social skills/values program from P-6. | The school has clear policies developed in collaboration with the school community taking into account emerging needs. | In the classrooms where drug-education is being taught the program is developmentally appropriate and ongoing. |
| Recommendations for future improvement Year 1 – Year 4 | Embed drug education in a whole school approach. Establish drug education outcomes that are appropriate to the school context and contribute to the overall goal of minimising drug-related harm. | Continue to provide a safe, supportive environment that promotes the prevention or reduction of drug related harm and increases parent engagement in the drug-ed program. | These policies will require review and be a focus in year 3 of the plan. | Increase the confidence and competence of teachers to deliver sequential drug-education, through interactive teaching and learning activities, P-6. |

Date: _______________

| Year 1 sample Happy Valley Primary School |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Theme area | # Recommended Actions What needs to be improved | How the activities, budget, equipment, IT, learning time, learning space | Who the individuals or teams responsible for implementation | When the date, week, month, term, year for completion |  | Achievement milestones the practice measures or lead indicators that describe success |
| Comprehensive and evidence-based practice | Embed drug education in a whole school approach. Establish drug education outcomes that are appropriate to the school context and contribute to the overall goal of minimising drug-related harm. | Increase awareness of effective drug education approach by viewing and discussing Drug Education in Schools (Steve Allsop) video. | Core Team to borrow video/DVD from SPO. | Early Term 1 |  |  |
|  |  | Survey given to classroom teachers to determine drug education topics currently being taught and resources used. | Core Team & Team Leaders. | Early term 1 |  | Overview of current teaching practices in drug education. Catalogue of drug education resources and location. |
| Positive school climate and relationships | Continue to provide a safe, supportive environment that promotes the prevention or reduction of drug related harm and increases parent engagement in the drug-ed program. | Use the school newsletter to communicate drug information to parents. | Core team leader to provide articles to office staff. | Terms 3&4 |  | Consistent messages to parents regarding drug education. |
| Targeted to needs and context | These policies will require review and be a focus in Year 3. |  |  |  |  |  |
| Effective pedagogy | Increase the confidence and competence of teachers to deliver sequential drug-education, through interactive teaching and learning activities, P-6. | Invite SPO to deliver drug education activities to level teams showcasing interactive activities appropriate for each level. | Core Team Leader to invite SPO. | Mid Term 2 |  | By the end of term 2 all staff will have the confidence to use interactive drug education activities in their classrooms. |
|  |  | Teachers to trial appropriate activities for their grade level with the assistance of the Core Team. | Core Team and all classroom teachers. | Early Term 3 |  | By the end of term 3 all teachers will be using interactive drug education activities. |
| Year 2 sample Happy Valley Primary School (To be completed in more detail at the end of Year 1 in preparation for Year 2) |  |  |  |  |  |  |
| Theme area | # Recommended Actions What needs to be improved | How the activities, budget, equipment, IT, learning time, learning space | Who the individuals or teams responsible for implementation |  | When the date, week, month, term, year for completion | Achievement milestones the practice measures or lead indicators that describe success |
| Comprehensive and evidence-based practice | Embed drug education in a whole school approach. Establish drug education outcomes that are appropriate to the school context and contribute to the overall goal of minimising drug-related harm. | Develop a comprehensive sequential drug education curriculum program mapped to VELS. | To be completed in detail prior to Year 2 |  |  |  |
| Positive school climate and relationships | Continue to provide a safe, supportive environment that promotes the prevention or reduction of drug related harm and increases parent engagement in the drug-ed program. | Begin the training of Year 6 students in Talking Tactics Together in order to facilitate a Parent Engagement evening. | Core Team to invite SPO to train Year 5/6 teachers. |  |  | Evaluation of parents attending TTT night. |
| Targeted to needs and context | To be completed in detail prior to Year 2 |  |  |  |  |  |
| Effective pedagogy | Drug education training for all health/pastoral care teachers at all levels which will include interactive pedagogies. | Training for new staff. Develop sequential drug ed units for each year level and trial lessons. |  |  |  | By the end of term 3 all teachers will be using interactive activities to ensure sequential, comprehensive drug education. |
| Year 3 sample Happy Valley Primary School (To be completed in more detail at the end of Year 2 in preparation for Year 3) |  |  |  |  |  |  |
| Theme area | # Recommended Actions What needs to be improved | How the activities, budget, equipment, IT, learning time, learning space | Who the individuals or teams responsible for implementation | When the date, week, month, term, year for completion |  | Achievement milestones the practice measures or lead indicators that describe success |
| Comprehensive and evidence-based practice | Embed drug education in a whole school approach. Establish drug education outcomes that are appropriate to the school context and contribute to the overall goal of minimising drug-related harm. | Some appropriate recommend actions may include: Review Evaluate Monitor Discuss Amend Continue Reflect Identify | To be completed in detail prior to Year 3 |  |  |  |
| Positive school climate and relationships | Continue to provide a safe, supportive environment that promotes the prevention or reduction of drug related harm and increases parent engagement in the drug-ed program. | Continuous monitoring and evaluation of your drug education program, against the strengths and recommendations from your review, will inform the drug education plan for year 3 and year 4. |  |  |  |  |
| Targeted to needs and context | These policies will require review and be a focus in year 3 of the plan. | Review of current drug related policies and procedures - amend where necessary in line with DEECD advice. See the Drug Use page of the School Policy and Advisory Guide: www.education.vic.gov.au/management/governance/spag/safety/drugprevention/druguse.htm Review medications policy - see the Medication page of the School Policy and Advisory Guide: www.education.vic.gov.au/management/governance/spag/health/caresupport/medication.htm After approval by school council, publicise amended medication policy in parent newsletter. | Working Group to include core team and representatives of leadership team. | Term 1, ready to be presented to school council in early term 2. |  | All staff understand procedures in relation to drug related incidents. Parents will be familiar with Medications Policy and the policy is observed when medication is brought to school by students. |
| Effective pedagogy | To be completed in detail prior to Year 3 |  |  |  |  |  |
| Year 4 sample Happy Valley Primary School (To be completed in more detail at the end of Year 3 in preparation for Year 4) |  |  |  |  |  |  |
| Theme area | # Recommended Actions What needs to be improved | How the activities, budget, equipment, IT, learning time, learning space | Who the individuals or teams responsible for implementation | When the date, week, month, term, year for completion |  | Achievement milestones the practice measures or lead indicators that describe success |
| Comprehensive and evidence-based practice |  |  |  |  |  |  |
| Positive school climate and relationships | To be completed in detail prior to year 4 |  |  |  |  |  |
| Targeted to needs and context |  |  |  |  |  |  |
| Effective pedagogy |  |  |  |  |  |  |